## Anticipated Cost Report (2)
Council on Aging Buidling
Anticipated Cost Report
November 27, 2023
BUDGET LINE + VENDOR |  |  | Funding |  |  |  | BUDGET |  |  |  |  | COMMITMENTS |  |  |  | EXPOSURES & FORECAST |  |  |  |  | ESTIMATE AT COMPLETION |  |  | INVOICED
Cost Code | Budget Item | Vendor(s) | Original Budget | Reallocations | Total Revised
[7 empty] | Total Project Cost Summary |  | Original Budget | Revised Budget |  | Commitments | Change Orders | Total Commitments |  | Forecasted Exposures | Forecasted Unpurchased Scope | Estimate to Complete (ETC) | Notes |  | Estimate at Completion (EAC) | Variance Under/(Over) |  | Total Invoiced
0.00 - Funding Sources
0.01 | FY16 Approved Funding | General use source | 470000 | -470000 | 0 |  | 1.0 Soft Cost |  | 2368362 | 2368362 |  | 164200 | 0 | 164200 |  | 0 | 0 | 0 |  |  | 164200 | 2204162 |  | 1420094
0.02 | FY21 Approved Funding | General use source | 150000 | -150000 | 0
0.03 | FY23 Approved Funding | General use source | 11000000 | -811731 | 10188269 |  | 2.0 Technology |  | 250000 | 250000
0.04 | Friends of COA -Estimated Donation | General use source | 100000 |  | 100000
0.05 | Additional funding | *clarify source | 500000 |  | 500000 |  | 3.0 Furniture & Equipment |  | 0 | 0 |  | 0 | 0 | 0
0.06 | AARPA Funds - Fiber | Restricted use - Fiber/Internet | 50000 |  | 50000
0.07 | AARPA Funds - AV & Security | Restricted use - AV & Security | 250000 |  | 250000 |  | 4.0 Construction |  | 8923562 | 8923562
0
0.08 | Funding Delta | Available funding/(Funding shortfall) |  |  | 0 |  | 5.0 Ancillary Items |  | 45000 | 45000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
0
| * Flag restricted use of funding |  |  |  | 0 |  | 6.0 Contingencies |  | 811731 | 811731 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| * Flag each funding source's use, when approved etc. |  |  |  | 0
| *Reallocate funding to individual Cost codes |  |  |  | 0
[5 empty] | 0 |  | Total Project Cost Totals |  | 12398655 | 12398655 |  | 164200 | 0 | 164200 |  | 0 | 0 | 0 |  |  | 164200 | 2204162 |  | 1420094
0.00 - Funding Sources Subtotal |  |  | 12520000 | -1431731 | 11088269
[7 empty] | Original Budget | Approved Changes | Reallocations | Total Revised |  | Commitments | Change Orders | Total Commitments |  | Forecasted Exposures | Forecasted Unpurchased Scope | Estimate to Complete (ETC) | Notes |  | Estimate at Completion (EAC) | Variance Under/(Over) |  | Total Invoiced
1.00 - Soft Costs
Column1 | Budget Item | Vendor(s) | Original | Reallocations | Total Revised | Column2 | Original Budget | Approved Changes | Reallocations3 | Total Revised4 | 5 | Commitments | Change Orders | Total Commitments | 6 | Forecasted Exposures | Forecasted Unpurchased Scope | Estimate to Complete (ETC) | Notes | 7 | Estimate at Completion (EAC) | Variance Under/(Over) | Column8 | Total Invoiced
1.01 | Architecture & Engineering | DAI
Enabling/feasibilty/Diligence subcategory
1.01 | Architecture & Engineering | DAI
1.02 | Amendment 1 |  |  | 164200 | 164200 |  | 164200 |  |  | 164200 |  | 164200 |  | 164200 |  | 0 |  | 0 |  |  | 164200 | 0 |  | 164200
1.03 | Amendment 2 |  |  | 455800 | 455800 |  | 767550 |  |  | 767550 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 767550 |  | 647646
1.04 | Amendment 3 |  |  |  | 0 |  | 112300 |  |  | 112300 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 112300 |  | 112300
1.05 | Amendment 4 |  |  |  | 0 |  | 73000 |  |  | 73000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 73000 |  | 73000
1.06 | Pending Amendment 5 (T&M) |  |  |  | 0 |  | 216000 |  |  | 216000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 216000 |  | -
1.1 | Interior Design | Elaine Bello |  |  | 0 |  | 9975 |  |  | 9975 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 9975 |  | 9975
1.2 | FF&E Specifications | Elaine Bello |  |  | 0 |  | 9000 |  |  | 9000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 9000 |  | -
1.3 | Civil Engineering | included in DAI |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  | -
1.4 | Geotechnical Engineering | included in DAI |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  | -
1.5 | Lighting Consultant | included in DAI |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  | -
1.6 | Owner's Project Management | City Point |  |  | 0 |  | 365000 |  |  | 365000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 365000 |  | 266325
1.7 | Hazardous Materials | TBD |  |  | 0 |  | 77000 |  |  | 77000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 77000 |  | 750
1.8 | A/V Consultant | Access AV |  |  | 0 |  | 7950 |  |  | 7950 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 7950 |  | 7950
1.9 | Archeologist | PAL |  |  | 0 |  | 9998 |  |  | 9998 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 9998 |  | -
1.11 | Commissioning - CPP estimated value | TBD |  |  | 0 |  | 40000 |  |  | 40000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 40000 |  | -
1.12 | Acoustic Consultant | Cavanaugh Tocci |  |  | 0 |  | 10000 |  |  | 10000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 10000 |  | 10000
1.13 | Energy Consultant - Building Envelope | Harley Engergy Consutling |  |  | 0 |  | 2250 |  |  | 2250 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 2250 |  | 2250
1.14 | Amendment 1 |  |  |  | 0 |  | 4500 |  |  | 4500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4500 |  | 4275
1.15 | Amendment 2 |  |  |  | 0 |  | 7875 |  |  | 7875 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 7875 |  | 6863
1.16 | Traffic Assessment | TEC |  |  | 0 |  | 16500 |  |  | 16500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 16500 |  | 16500
1.17 | Amendment 1 - MassDOT Cooridnation | TEC |  |  | 0 |  | 3500 |  |  | 3500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 3500 |  | 1680
1.18 | Soil Communication Testing/Sub Slab Depressurization Design | Storch Radon |  |  | 0 |  | 500 |  |  | 500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 500 |  | 500
1.19 | PM&C 100% CD Estimate | Services inc. |  |  | 0 |  | 15000 |  |  | 15000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 15000 |  | 15000
1.21 | OTHER SOFT COSTS |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  | -
1.22 | Furniture & Equipment - Town value | Town of Wayland |  |  | 0 |  | 280000 |  |  | 280000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 280000 |  | -
1.23 | Kitchen Design & Equipment - Town value | Town of Wayland |  |  | 0 |  | 90000 |  |  | 90000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 90000 |  | 1200
1.24 | Printing & Advertising | TBD |  |  | 0 |  | 4000 |  |  | 4000 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4000 |  | 1955
1.25 | ConCom/Planning Board Peer Reviewer & second Review | DGT Associaties |  |  | 0 |  | 8210 |  |  | 8210 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 8210 |  | 8210
1.26 | Interior Display Feasibility Study | Rachel Robinson |  |  | 0 |  | 4500 |  |  | 4500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4500
1.27 | Landscape Plan | Fast Signs |  |  | 0 |  | 4620 |  |  | 4620 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4620 |  | 4620
1.28 | Signage Design | Professional Fire Systems |  |  | 0 |  | 664 |  |  | 664 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 664 |  | 625
1.29 | Flow Test | Tighe & Bond |  |  | 0 |  | 600 |  |  | 600 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 600 |  | 600
1.31 | Permitting and Design | Kang |  |  | 0 |  | 24841 |  |  | 24841 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 24841 |  | 24841
1.32 | Programming Study | Wayland Excavating |  |  | 0 |  | 17200 |  |  | 17200 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 17200 |  | 17200
1.33 | Pipe Repair | BMC |  |  | 0 |  | 1500 |  |  | 1500 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 1500 |  | 1500
1.34 | Roof Structural Report | Anderson & Kreiger |  |  | 0 |  | 2413 |  |  | 2413 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 2413 |  | 2413
1.35 | Anderson & Kreiger | Richard Testa |  |  | 0 |  | 2937 |  |  | 2937 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 2937 |  | 2937
1.36 | Soil Sampling | DG Jones |  |  | 0 |  | 1280 |  |  | 1280 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 1280 |  | 1280
1.37 | SD Cost Estimate | Beta Group |  |  | 0 |  | 3250 |  |  | 3250 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 3250 |  | 3250
1.38 | COA Study (2022) | Xfer |  |  | 0 |  | 4078 |  |  | 4078 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4078 |  | 4078
1.39 | Miscellaneous fees from 2016 |  |  |  | 0 |  | 6171 |  |  | 6171 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 6171 |  | 6171
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
[5 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  | 0 | 0
1.00 - Soft Costs Subtotal |  |  |  | 620000 | 620000 |  | 2368362 | 0 | 0 | 2368362 |  | 164200 | 0 | 164200 |  | 0 | 0 | 0 |  |  | 164200 | 2204162 |  | 1420094
2.00 - Technology
Column1 | Budget Item | Vendor(s) | Original | Reallocations | Total Revised | Column2 | Original Budget | Approved Changes | Reallocations3 | Total Revised4 | Column3 | Commitments | Change Orders | Total Commitments | Column4 | Forecasted Exposures | Forecasted Unpurchased Scope | Estimate to Complete (ETC) | Notes | Column5 | Estimate at Completion (EAC) | Variance Under/(Over) | Column8 | Total Invoiced
| Technology / IT / Phones | [5 empty] | 50000 |  |  | 50000 |  |  |  | 0 |  |  | 50000
| A/V Equipment & Installation | [5 empty] | 200000 |  |  | 200000 |  |  |  | 0 |  |  | 200000
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
2.00 - Technology Subtotal |  |  | 0 | 0 | 0 |  | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 0 |  | 0 | 250000 | 0 |  |  | 0 | 651337 |  | 146648
3.00 - Furniture & Equipment
Column1 | Budget Item | Vendor(s) | Original | Reallocations | Total Revised |  | Original Budget | Approved Changes | Reallocations3 | Total Revised4 |  | Commitments | Change Orders | Total Commitments |  | Forecasted Exposures | Forecasted Unpurchased Scope | Estimate to Complete (ETC) | Notes |  | Estimate at Completion (EAC) | Variance Under/(Over) | Column8 | Total Invoiced
3.00 - Furniture & Equipment Subtotal |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 74054 |  | 69515
4.01 - Construction
[7 empty] | 0 |  |  | 0
| Hardcosts | [5 empty] | 8829000 |  |  | 8829000
| Interior Demolition | [5 empty] | 94562 |  |  | 94562 | [13 empty] | 94562
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
4.00 Construction Subtotal |  |  | 0 | 0 | 0 |  | 8923562 | 0 | 0 | 8923562 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 94562
[7 empty] | 0 |  |  | 0
5.01 - Ancillary Items
| Utility Backcharges | [5 empty] | 15000 |  |  | 15000
| Moving Expenses/Storage | [5 empty] | 5000 |  |  | 5000
| BR Policy | [5 empty] | 25000 |  |  | 25000
0
0
0
0
Subtotal | [6 empty] | 45000 | 0 | 0 | 45000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
6.01 - Contingencies
[10 empty] | 0 |  |  |  | 0
| Project Contingency |  |  | 811731 |  |  | 811731 |  |  | 811731 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
0
Subtotal | [6 empty] | 811731 | 0 | 0 | 811731 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
Grand Total |  |  | 0 | 0 | 0 |  | 12398655 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0
TRUE
Note on I29: Filter blanks once budget is complete

## Schedule
Phases | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Approvals | bar: 2022 Jan to 2024 Jan
Design | bar: 2022 Feb to 2023 Sept
Estimating | bar: 2022 May to 2023 Sept
Procurement | bar: 2023 Sept to 2023 Dec
Construction | bar: 2024 Jan to 2024 Dec
Phases | 2022 Jan: 2016; 2022 Feb: 2017 - 2020; 2022 Mar: 2021; 2022 Apr: 2022; 2023 Apr: 2023; 2024 Apr: 2024
| Jan - Dec | Jan - Dec | Jan - Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Approvals | « |  | « | bar: 2022 Jan to 2024 Jan
Design | bar: 2022 Feb to 2023 Sept
Estimating | bar: 2022 May to 2023 Sept
Procurement | bar: 2023 Sept to 2023 Dec
Construction | bar: 2024 Jan to 2024 Dec
Phases | 2024
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Approvals | bar: 2024 Jan to 2024 Apr; 2024 Aug to 2024 Dec
Site Improvements | bar: 2024 Jan to 2024 Oct
Interior Construction | bar: 2024 Jan to 2024 Dec
Substantial Completion | bar: 2024 Dec

## WaylandDashboard
Project Information | [16 empty] | Decisions / Actions Next 30/60 Days
|  |  | Wayland Council on Aging and Community Center Project | [13 empty] | Item | Description |  |  |  |  | BIC/Responsible |  | Item | Description |  | BIC/Responsible
Project Name: | [7 empty] | Project Description: |  |  | This project includes renovations to the existing building located at 8 Andrew Ave. and developing a new Council on Aging and Community Center. Improvements include parking areas, sidewalks that connect Andrew Ave. and Lillian Way, patio, stormwater management system, site grading, utility connections, solar canopies, landscaping, hardscaping, and lighting. | [5 empty] | 1 | Confirm PMBC to review and recommend approval of change orders |  |  |  |  | PMBC |  | 6
Project Department: |  |  | Public Buildings Department | [13 empty] | 2 | Review of OPM & Architect amendments - Currently in negotiation of fee |  |  |  |  | CPP/DAI/BK |  | 7
Project Type: |  |  | Renovation | [13 empty] | 3 | [7 empty] | 8
Project Phase: |  |  | Construction | [13 empty] | 4 | [7 empty] | 9
Owner Prj. Manager |  |  | HDR-City Point Partners | [13 empty] | 5 | [7 empty] | 10
Architect |  |  | DiGiorgio Architects
Construction Manager |  |  | Tower Construction |  |  |  |  | Appointed Members: |  |  | Ben Keefe - Public Buildings Director
Gross Square Feet (SF): |  |  | 12,000SF | [7 empty] | Bill Sterling - COA Working Group
Construction Start: |  |  | 2024-01-01 | [7 empty] | Greg Lusky - COA Representative
Construction Complete: |  |  | 2024-12-01
Total Project Cost Summary | [16 empty] | Total Project Cash Flow Projections
|  |  |  | Current Budget |  |  |  |  | Exposures & Forecast | [5 empty] | Invoiced |  |  |  | Projected | Projected | Actual | Actual |  | Rev Projected | Rev Projected
|  |  |  | A |  | B | A + B = C |  | D |  | E |  | D + E =F | C - F = G |  |  | Req | Month-Year | Cashflow | Cumulative | Cashflow | Cumulative |  | Cashflow | Cumulative |  | Total Budget Value
|  |  |  | Original |  | Budget | Revised |  | Total |  | Estimate to |  | Estimate at | Variance | Total Invoiced | As a % of Total | 1 | 2015 - 2016 | 32029.38 | 32029.38 | 32029.38 | 32029.38
Description |  |  |  | Budget |  | Adjustments | Budget |  | Commitments |  | Complete |  | Completion | Under/ |  | Project Cost | 2 | 2017 - 2020 | 36367.2 | 68396.58 | 36367.2 | 68396.58
[9 empty] | To date |  | (ETC) |  | (EAC) | (Over) |  |  | 3 | 2021-12-01 | 0 | 68396.58 | 0 | 68396.58
Funding | [16 empty] | 4 | 2022-12-01 | 815048.68 | 883445.26 | 815048.68 | 883445.26
0.0 Total Approved Funding |  |  |  | 12520000 |  | 0 | 12520000 | [9 empty] | 5 | January - April 2023 | 319458.17 | 1202903.43 | 319458.17 | 1202903.43
Total Project Cost Summary | [16 empty] | 6 | 2023-05-01 | 45133.99 | 1248037.42 | 22637 | 1225540.43
1.0 Soft Costs |  |  |  | 2114707 |  | 0 | 2114707 |  | 2114707 |  | 216861 |  | 2331568 | -216861 | 1633541 | 13.05% | 7 | 2023-06-01 | 43345.24 | 1291382.66 | 10981.92 | 1236522.35
2.0 Technology |  |  |  | 50000 |  | 0 | 50000 |  | 0 |  | 50000 |  | 50000 | 0 | 0 | 0% | 8 | 2023-07-01 | 34103.24 | 1325485.9 | 14869.5 | 1251391.85
3.0 Furniture |  |  |  | 280000 |  | 0 | 280000 |  |  |  | 280000 |  | 280000 | 0 | 0 | 0% | 8 | 2023-08-01 | 28729.63 | 1354215.53 | 14073.5 | 1265465.35
4.0 Construction |  |  |  | 8923562 |  | 0 | 8923562 |  | 8923562 |  | 96470 |  | 9020032 | -96470 | 0 | 0% | 9 | 2023-09-01 | 41803.1 | 1396018.63 | 36396 | 1301861.35
5.0 Audio/Visual |  |  |  | 200000 |  | 0 | 200000 |  |  |  | 200000 |  | 200000 | 0 | 0 | 0% | 10 | 2023-10-01 | 21496.81 | 1417515.44 | 147649.18 | 1449510.53
6.0 Kitchen Design & Equipment |  |  |  | 90000 |  | 0 | 90000 |  |  |  | 90000 |  | 90000 | 0 | 0 | 0% | 11 | 2023-11-01 | 116471.05 | 1533986.49 | 17314.17 | 1466824.7
7.0 Utility Backcharges |  |  |  | 15000 |  | 0 | 15000 |  |  |  | 15000 |  | 15000 | 0 | 0 | 0% | 12 | 2023-12-01 | 219414.83 | 1753401.32 | 50004.8 | 1516829.5
8.0 Moving Expenses/Storage |  |  |  | 10000 |  | 0 | 10000 |  | 0 |  | 10000 |  | 10000 | 0 | 0 | 0% | 13 | 2024-01-01 | 624963 | 2378364.32 | 45259.3 | 1562088.8 |  |  | 1562088.8
9.0 Builiders Risk Insurance |  |  |  | 25000 |  | 0 | 25000 |  |  |  | 25000 |  | 25000 | 0 | 0 | 0% | 14 | 2024-02-01 | 724603 | 3102967.32 | 71451.93 | 1633540.73 |  | 148126.25 | 1710215.05
10.0 Eversource Utility Work |  |  |  | 17795 |  | 0 | 17795 |  | 17795 |  | 0 |  | 17795 | 0 | 0 | 0% | 15 | 2024-03-01 | 913552 | 4016519.32 | 0 |  |  | 1287625.25 | 2997840.3
11.0 Ancillary Items |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 2024-04-01 | 909014 | 4925533.32 | 0 |  |  | 1237625.25 | 4235465.55
Sub-Total Project Cost: |  |  |  | 11726064 |  | 0 | 11726064 |  | 11056064 |  | 983331 |  | 12039395 | -313331 | 1633541 |  | 17 | 2024-05-01 | 1004988 | 5930521.32 | 0 |  |  | 1081662.25 | 5317127.8
6.0 Contingencies |  |  |  | 793936 |  | 0 | 793936 |  |  |  | 480605 |  | 480605 | 313331 |  |  | 18 | 2024-06-01 | 1163463 | 7093984.32 | 0 |  |  | 1240137 | 6557264.8
Total Project Cost: |  |  |  | 12520000 |  | 0 | 12520000 |  | 11056064 |  | 1463936 |  | 12520000 | 0 | 1633541 | 13.05% | 19 | 2024-07-01 | 1161131 | 8255115.32 | 0 |  |  | 1161131 | 7718395.8
[17 empty] | 20 | 2024-08-01 | 1062488 | 9317603.32 | 0 |  |  | 1139162.25 | 8857558.05
Funding - Total Project Cost Variance | [6 empty] | 0 |  |  | 0% | Unallocated Funding | [5 empty] | 21 | 2024-09-01 | 925658 | 10243261.32 | 0 |  |  | 1002332.25 | 9859890.3
Prior Month TPC |  |  | 12520000 |  | Month over Month Variance |  |  |  | 0 | [7 empty] | 22 | 2024-10-01 | 766653 | 11009914.32 | 0 |  |  | 920001.25 | 10779891.55
[6 empty] | Estimated | Quoted |  | Approved | [7 empty] | 23 | 2024-11-01 | 674792 | 11684706.32 | 0 |  |  | 828140.25 | 11608031.8
Approved, Quoted and Estimated Change Orders: | [5 empty] | 313331 | 0 |  | 0 |  | Current Month | [5 empty] | 24 | 2024-12-01 | 469125.67 | 12153831.99 | 0 |  |  | 545800 | 12153831.8
[6 empty] | 0 | 0 |  | 0 |  | Prior Month | [5 empty] | 25 | 2025-01-01 | 318500 | 12472331.99 | 0 |  |  | 318500 | 12472331.8
[6 empty] | 313331 | 0 |  | 0 |  | Variance | [5 empty] | 26 | 2025-02-01 | 28834 | 12501165.99 | 0 |  |  | 28834 | 12501165.8
TPC Notes & Context | [16 empty] | 27 | 2025-03-01 | 18834 | 12519999.99 |  |  |  | 18834 | 12519999.8
1 | Potential Upcoming change - Risk register item #7 - Tower requested to reconfigure interior trenching. Estimated change amount $10,000
2 | Potential Upcoming Change - Risk register item #8 - Add additional strutural support to roof sections that solar panels are to be installed. Estimated total change $10,000
3 | Water Service Change - the proposed line had been abandoned and new connection had to be established. PCO $39,117.50 (in review/negotiation)
4 | Removal of exisitng concrete rings discovered during site work. PCO $16,826.40 (In review/negotiation)
5 | Change in snow guard type suitable for Metal Roof alternate. PCO $20,525.87 (in review/negotiation) | [15 empty] | Progress Images
Risk Register
Item | Description |  |  |  |  | ROM | BIC/Responsible |  | Status |  |  |  |  | Likelihood | Financial | Schedule
2 | Supply Chain (long lead equipment) | [5 empty] | Tower |  | submittal process ongoing |  |  |  |  | Medium | Low | Medium
3 | LSP Site Monitoring | [5 empty] | Tower |  | Ongoing site review with CMG & ERM |  |  |  |  | Medium | Medium | Medium
4 | Site Work - Archeology | [5 empty] | Tower / PAL |  | PAL monitoring |  |  |  |  | Low | Low | Low
6 | Solar coordination | [5 empty] | Solect |  | Coordination with Solect on canopy footing & roof installation |  |  |  |  | Medium | Medium | Medium
7 | Interior Trenching |  |  |  |  | 10000 | Tower |  | Tower developing proposal |  |  |  |  | Medium | Medium | Low
8 | Roof reinforcement |  |  |  |  | 10000 | DAI |  | Design amendment in review |  |  |  |  | High | Medium | Low
9 | Concrete block found in interior slab | [5 empty] | Tower |  | Tower chipping at block by T&M |  |  |  |  | High | High | Medium
Project Schedule Summary & Milestones
Major Milestone Targets
Date |  | Description | [7 empty] | Status |  | Notes
Jan-April-24 |  | Submittal Process | [7 empty] | Ongoing
2024-07-24 |  | Interior Permanent Power | [7 empty] | Ongoing
Aug-Sept-24 |  | Curbing and Sidewalks. Followed by paving in October | [7 empty] | Ongoing
Aug-Dec-24 |  | Inspections | [7 empty] | Ongoing
2024-10-24 |  | Interior Finishes | [7 empty] | Ongoing
2024-12-24 |  | Substantal Completion and Closeout | [7 empty] | Ongoing |  | Substantial Completion target date - 12/2/24
2024-12-01 |  | Construction Complete | [7 empty] | Ongoing
Note on M3: Brief Desciprtion of project. Ex. Renovation of existing x SF buidling scope includes new roof, finishes, etc.
Note on D5: Repair Renovation New Construction
Note on D6: Diligence Funding Approvals Design Bidding Construction Punchlist/Complete
Note on D11: Month Year December 2023
Note on D12: Month Year December 2023

## Sheet1
132 | 3 | 37
140 |  | 16
130
113
229
243
238

## Funding Schedule
2024-02-28
Item | Date | Funding Source | Restrictions | Value | Notes
1 |  | FY16 Approved Funding | General use source | 470000
2 |  | FY21 Approved Funding | General use source | 150000
3 |  | FY23 Approved Funding | General use source | 11000000
4 |  | Friends of COA -Estimated Donation | General use source | 100000
5 |  | Additional funding | *clarify source | 500000
6 |  | AARPA Funds - Fiber | Restricted use - Fiber/Internet | 50000
7 |  | AARPA Funds - AV & Security | Restricted use - AV & Security | 250000
12520000